## Sheet1
PG Full Stack Web Development
PROJECT FOR PHASE 2
TYPE OF ACTIVITIES | PLAN DURATION (DAY)
ANALYSIS | 5 DAYS
WRITING CODE | 5 DAYS
TESTING THE SOFTWARE | 3 DAYS
DOCUMENTATION | 2 DAYS
START DAY | END DAY | ACTIVITIES DESCRIPTION | PERSON IN CHARGE
2023-02-20 | 2023-02-25 | Analysis the system requirement | Project leader
2023-02-26 | 2023-03-03 | Prepare the system specification | Project leader
|  | Writing the code | Programmer
2023-03-03 | 2023-03-05 | Testing the software | Quality Assurance team
2023-03-06 | 2023-03-08 | Writing the documentation | Quality Assurance team
Formulas:
END DAY = +[START DAY]+5
START DAY = +[END DAY, row above]+1